DESIGN PARADIGM

A PROPOSAL FOR A

RESIDENTIAL AND COMMERCIAL DEVELOPMENT

May 2004

# To

Lincoln Property Company

2639 I Street, N.W., Washington, D.C. 20037

REPORT PREPARED BY:

1819 N. HOLLISTER STREET, ARLINGTON, Va 22205.   TEL: 703/532-2122

COPYRIGHT 1990 - 1997 © GIBSON & ASSOCIATES

COVER:

* DESIGN PARADIGM - OVER LONDON - GLC BUILDING

TABLE OF CONTENTS

i. - Executive Summary	4

Vision

Objective of the Proposal

Project Summary (Areas and Costs)

Project Funding Letter

Preliminary Funding Budget

Letter of Project Support DCHCD - 3/11/97

ii. - Watergate North - Project Introduction	7

Historical Background

Present Status of Project

Precedents for similar “Right of Way” Projects

Project Zoning

Project Potential

Section 1 - Site Maps	10

Local Map of District of Columbia

Map of Project Area - 1948

Aerial Photo - 1997

Section 2 - Site Photographs	13

View Toward Potomac and Watergate Complex

Howard Johnson Hotel - Site of Phase 1 Development

Barnhard Townhouses

Portion of Existing Site and Whitehurst Ramp Area

Miscellaneous Views (2)

Section 3 - Design	19

Site Design Plan of Watergate North - Phases 1,2, and 3

Site Design Sections - Phases 1,2 and 3

Site Layout

Phase 1 - Floor Plans

Project Sections

Typical Unit Layouts

TABLE OF CONTENTS (continued)

Section 4 - Implementation	20

- General Methodolgy

- Schedule for Unsolicited Proposal to DCHCD – Part A

Costs Associated with Part A

Cost per Week based upon Schedule for Part A

- Schedule for PUD Approval – Part B

Costs Associated with Part B

Cost per Week based upon Schedule for Part B

Appendix	                                                                                                  23.

Glossary

General Notes

Expense Assumptions

Project Equity and Ownership

Resumes of Participants:

- Dale Barnhard / Barnhard Realty

- Gibson and Associates

- Fred L. Greene Associates

- Corporate Economic Strategies, Inc.

Listing of similar “Right of Way “ Projects

Specific Examples of ROW Projects

Tax Incentives for Enterprise Zone from DC

Briggs Montgomery School at Watergate North

EXECUTIVE SUMMARY

VISION

Watergate North, L.L.C. envisions creating an historically appropriate neighborhood to anchor the west end of the Foggy Bottom community.  The project will transform the urban wasteland created by the I-66 Freeway interchange built in the 1960’s back into a livable residential community.  The project is bounded by L Street to the North, Potomac Parkway to the West, Virginia Avenue to the South and 26th Street to the East.

The mix of uses will consist of luxury condominium units, rental apartments, market rate condominium apartments, an all suites hotel, a K-6 Elementary School and supporting commercial space to be assembled in a single unified and cohesive neighborhood. Present planning calls for three phases of development.  The proposed assembled land area is extremely well located.  It lies within a short walking distance from Georgetown, the Kennedy Center for Performing Arts, the Mall and the Foggy Bottom Metro stop.  The project is directly across the street from the well known Watergate Complex.  The proximity to Federal and DC government agencies is an additional plus.  Most key Washington tourist attractions are quickly and easily accessible from this location.

OBJECTIVE OF PROPOSAL

The objective of this proposal is to acquaint you with the potential of this project and to provide the necessary supporting information upon which decisions can be made.  The proposed luxury residential units will provide upscale living environments for those desiring the amenities as well as the location.  Studies indicate a strong market for this type of property in such a key location.  The rental apartments and apartment condominiums will be a mix of market rate and affordable housing components.  The commercial space will cater to both resident traffic as well as pedestrians traveling through the adjacent areas of the project on a daily basis.  The all-suites hotel will serve the needs of the vacation visitors coming to the Capitol City as well as businessmen who find themselves here on a regular basis representing their company’s' interests. Associations, corporations, consultants, lobbyists, etc., have an ongoing need to be in the Capitol City on a regular basis, many,  for extended periods of time.  The opportunity to stay in a residence atmosphere rather than a conventional hotel room will be welcomed.  The all-suites hotel will provide this ambiance along with upscale services that are traditionally available from five star hotels. The Washington, D.C. is market is ready for this project type.

This project will require substantial funding to assemble the parcel and have sufficient funds to cover the cash outflow for expenses until pre-sales generate funds to complete the project.  It is anticipated that once the project is underway, pre-sales of the various types of units will provide positive cash flow.  While the buildings are being completed, additional pre-sales of the residence units will occur and add additional revenue.  The net revenue will be used to retire the invested capital as it becomes available. It is anticipated that it will require four years to sell out the entire residential component of the project.

The timing is good for negotiating the terms of this project with the DC government.   The city's current cash shortage, the need for an infusion of new revenue sources, the administration's review and reduction of federal funds for the City's budget, potential job creation for the city and additional property tax revenue all provide a window of opportunity for securing the land owned by the city.  The Developers are confident that the necessary approvals to do the project in its entirety can be obtained.  However, time is of the essence to finalize this effort.  This parcel of land, when assembled, is one of the largest, last (and let us say least recognized) and best pieces of land still available for this use in the CBD/Monuments Area.  It is well sited and can be assembled for a reasonable cost.

WATERGATE NORTH - PROJECT INTRODUCTION:

HISTORICAL BACKGROUND

Prior to 1960 the project site was the western edge of the neighborhood known as "Foggy Bottom" (a reference to the turn of the century when the Potomac River covered more land and this area was always foggy due probably to fossil fuel air pollution).  This neighborhood was separated from Georgetown by Rock Creek and the industrial uses at the waterfront.  The Whitehurst Freeway connected the K Street corridor to the Key Bridge and to the Western suburbs.

In the 1960's Interstate Highway 66 was built in Northern Virginia and connected to the Roosevelt Bridge.  The Washington side of the I-66 connections included the E Street Expressway and the Ramp complex to the Whitehurst Freeway.  The construction of these ramps resulted in the District of Columbia government expropriating land (approximately six city blocks) from the Foggy Bottom Residential neighborhood.  In so doing, the Briggs Montgomery School (a private school) was removed and many townhouse residences as well.  The project site (Squares 1, 4, 5 and 6) includes the last three residential units that remain, and these units are completely severed from the original neighborhood.

In the 1980's there was a popular movement to have the Whitehurst Freeway removed. as the Georgetown waterfront was developing and as the industrial uses had all but vanished. This movement did not succeed and the Whitehurst was renovated instead. This change in focus moved from the discussion of removing the elevated freeway to the removal of elevated ramps leading to Whitehurst Freeway but did not address the re-construction of the neighborhood originally devastated.  The disposition of this matter is now complete and there is good indication from the District Government that the plan by the consultants for the Dept. of Public Works is approved and the elevated ramps will remain for the foreseeable future.  Two existing ramps (now abandoned) will be removed.  Work on this project is scheduled for Summer 1997 and will be completed in 1988.

PRESENT STATUS OF THE PROJECT

The Developers are collaborating with the present Owners of a portion of the site (Square 5) specifically Mr. Dale Barnhard of Barnhard Realty.  Mr. Barnhard is in a good position to deal with the District of Colombia because of the way the city has treated him in the past and because his land is the only access to the balance of Square 5 land which is owned by the District of Colombia.  To this end the District of Colombia had previously requested that an unsolicited offer to purchase this land be made by this group.  We have responded affirmatively and the District of Columbia has approved our proposal subject to final design and a negotiated settlement.   Our offer will be in good faith and reasonable.

Additionally, the Developers will work with the owners of the parcels of land effected by this development and with adjoining property holders to reach an amicable solution to a difficult urban planning problem.

Informally, the Developers have approached the City regarding the overall development of the adjacent areas.  The Developers have obtained tentative positive reaction to their proposal to close "I" Street and to relocate the entrance ramp from Department of Public Works.  This must be formalized in a written agreement in order for this part of the project to proceed as proposed.  This street closing is crucial to the overall project and adds approximately 17,000 square of land to the total parcel, and the new ramp will occupy approximately 10,000 square feet in the revised location.

The Howard Johnson Hotel site (Square 6) can be an important part of the development.  The hotel is currently owned by Stuart Bernstein and it is believed that he will be a willing participant in the project development. Similarly, the Sunoco Gas Station land needs to be made part of the project.  The three townhouse sites are owned by Barnhard Realty with whom the Developers are working in this effort.

## PRECEDENTS

There are many precedents for projects that have been built over and around highways (Right of Way Projects).  These projects are relatively common in urban areas where land is scarce and here in Washington that is also true in the Central Business District and nearby residential areas.  In Washington, we have the examples of L’Enfant Plaza which is built over access roads to I-395 and city grid streets and the Columbia Apartment Complex spanning over I-295 at 3rd and H Streets.  In the Appendix we have listed over 40 similar projects worldwide that are considered Right of Way projects.

At Watergate North we are fortunate that the access roadways are used only by cars and the hours of heavy use are limited to short duration’s at morning and evening rush hours.  Improvements contemplated to the West End of the E Street Expressway will do much to relieve some of the present congestion during rush hours.

PROJECT ZONING

We have taken a very conservative approach in the development of the project utilizing a Floor Area Ratio (FAR)  of 6.0 based upon the status of the surrounding residential area.  The site will be filed as PUD and would have to go to the Board of Zoning Appeals and other authorities having jurisdiction because of the street closing, transfer of DC land and other issues.

PROJECT POTENTIAL

The Watergate North project is ideally located in the prestigious Northwest quadrant of Washington, DC overlooking the Potomac River with only United States Park Land between the site and the river.  The site is close to Georgetown, across the street from the Watergate Complex and nearby to the Kennedy Center.  There is little question that potential residents will be willing to pay top prices for the advantages of living in this ideal location.

Phase I includes high-end condominium apartments and market rate apartments (421 units) and supportive commercial component.  Sale of condominium apartments and rentals of apartment units is projected to be complete within two years.  Commercial space served by below grade parking (also accessible and available to residential units) will be leased on an annual basis. The developer recommends design of units to allow flexibility between the quantity of condominiums and rental units.

Phase II is envisioned  as condominium apartments and market rate apartments (375 units) and supportive commercial component.  Sale of condominium apartments and rentals of apartment units is projected to be complete within two years.  Commercial space served by below grade parking (also accessible and available to residential units) will be leased on an annual basis. The developer recommends design of units to allow flexibility between the quantity of condominiums and rental units.  The developers have tentative commitments for 100-150 units at this time.

Phase III is an all-suites hotel (260 units), commercial space with a high quality sports club and access to outdoor activities.

Project Summary (Area and Construction Calculations) follows:

SECTION 1 - SITE MAPS

A. - LOCAL MAP OF DISTRICT OF COLUMBIA

CURRENT 1997 MAP OF LOCAL WASHINGTON D.C. AREA

B. - 1948 MAP OF PROJECT AREA (Courtesy of National Geographic, Inc.)

Note that the original site area was a typical Washington, DC street grid with the Briggs Montgomery School anchoring the West End of Foggy Bottom.

C. - AERIAL PHOTOGRAPH OF PROJECT AREA

NORTH >

SECTION 2 - SITE PHOTOGRAPHS

View of Howard Johnson Hotel from Virginia Avenue.

View of Foggy Bottom from North East with rear of Howard Johnson in midfield.

SECTION 3 - DESIGN

SITE DESIGN AND PROGRAM:

The accompanying drawing indicates the Site Design with the corresponding building floor

areas and unit composition.  It has been designed in order to utilize the site area to the maximum yet utilizing aesthetic and practical criteria to arrive at an elemental composition that belies its large scale.  Once the actual Architectural designs and drawings are completed and all necessary meetings with the DC Board of Zoning appeals, the Fire Marshall, Building Permit Office, and Board of Building Appeals are completed; then, the actual finalized building configuration and design will emerge. When this is known, the actual quantitative criteria relative to the physical properties can be accurately quantified.

SECTION 4 - IMPLEMENTATION

IMPLEMENTATION - GENERAL:

Watergate North will require a disciplined approach to execution of the implementation procedures which are critical to achieve the return on investment which is time dependent.  A timeline is provided herein depicting the major steps required for the Phased development.  The steps outlined provide for a well timed and coordinated effort which will create positive results in the form of sales and occupancy of the units and rental areas.  Although certain key parts of this work will be complex in nature, the rather basic interrelationship of progress depicted can be readily achievable within the time frame allowed.  It is probable that with careful timing, the Watergate North development could be put on stream in record time due to its particularly high visibility.  Steps in the procedural outline are described in more detail below:

1. Establish Legal Project Entities:

This will include the formation of corporations, partnerships, and other viable project vehicles required to execute the transactions and retention’s of ownership and liability required.

2. Feasibility Analysis:

This will include further analysis, comprehensive data gathering and related studies as required to provide for certain financing requirements. Key research and marketing analysis required will also be prepared at this time.

3. Legal and Land Transactions:

Purchase agreements and land acquisition will be executed during this time.

4. Survey and Setup:

Survey crews, finalized detailed topographic, utility and related documentation for land transaction purposes as well as for later engineering usage will be compiled.

5. Project/Zoning/Appeals/Easements:

All necessary applications for municipal permissions, appeals, and related  activities will be transacted during this period.  Also, certain key efforts relating to any easements and permissions in the provision of utilities and related.  It is understood that this work will incorporate the efforts of the legal, architectural, and engineering professionals involved.

6. Architectural/Engineering Design:

Preparation of initial Design submissions including all necessary sizing and heights, etc.  Engineering design will be provided as required to submit necessary documentation for traffic, utility, and basic municipal approvals. Also, project models and three dimensional perspective drawings as necessary for public relations and presentation purposes will be executed.

7. Architectural/Engineering Approvals:

The utilization of the work prepared through the Design process will be presented for agency review and approvals.  A continuous process of alterations and detailed responses/rebuttals will ensue culminating in the project approval to allow for building permit review of the finalized plans and specifications.

8. Set up Sales:

Timeshare and residential sales will proceed with the establishment of a bonafide marketing and sales organization to insure the undertaking proceeds as planned.  The direction of the sales team will be coordinated by the Project Executive and will be located on the project site.

9. Complete Model Unit(s):

The construction of on site model unit(s) will be accomplished at locations on the site that will not hinder later work and will allow for purchaser familiarity with the final product.

10. Architectural/Engineering Construction Documents:

This will include the Architectural and Engineering plans sufficient to obtain building permits for the work.  These will be prepared and certified according to local codes and ordinances.  The plans will be phased in preparation so that a Fast Track construction methodology will allow for immediate results in the construction process.

11. Residential Sales:

A sales force operating from the model unit(s) area will be responsible for sales and marketing efforts involved.

12. Hotel (all-suites):

The developers will secure the land and negotiate with a hotel chain for the operation of the hotel and sports club.

13. Purchase Site Properties:

The land assembly for the properties necessary will be conducted during this period.

14. Demolition at Site:

Selective demolition of on site elements will be conducted as required to achieve the necessary result required by the construction documents.

15. Commercial and other rentals:

Commercial space within the complex will be leased to tenants providing primarily resident required services.  It is anticipated that a first rate health club and restaurant(s) will be among the primary users of these spaces.

16. Building Operations/Management:

The project management and operations will be handled in an organized manner from the start.  The building professionals handling this portion of the operation will be familiar with all elements of the residential property management.

17. Site Work/Utilities:

The initial phase of construction will include construction of over roadway cover structures, grading and subsurface work.

18. Site Work:

Continuing throughout the Construction process, this will include all finalized landscape and related work.

19. Building Construction:

The construction beginning with foundations through finished architectural spaces including interior furnishings of timeshare units. Delivery of ready-for-occupancy areas and buildings.

20. Tenant Improvements:

Commercial space for rent will be outfitted with full construction accouterments to include finished floors, walls, and ceilings - fully accessorized with working mechanical and electrical systems ready for occupancy .

22. Project Construction Close-out:

The project acceptance for the Owner will be accomplished by a certain date for the purposes of substantial completion.  In reality, this acceptance procedure will be phased through a period of occupancies and acceptances of each of the major buildings in this complex and individual spaces therein.

APPENDIX:

GENERAL NOTES:

The Watergate North development data included herein has been prepared based on certain general assumptions concerning the site, costs of various types, expenses, vacancy rates, etc.  The basic descriptions of the major factors involved in the calculations are contained within the main body of this report, however, we are providing additional detail in the following items.

ASSUMPTIONS

·	Costs based on 1997 Construction and pricing data.

·	Prices for real estate valuation based on available information at the time of report preparation.

·	Estimates for sales rates and levels of absorption of the total facility based on expected assimilation and realistic sales/marketing program projections.

·	Construction costs based on current market rates.

·	Hotel construction costs include furnished suites complete and ready for occupancy.

RATES AND FEES

·	Fees for professional services and related services are based on market rates in the Washington DC area.

OPERATIONS

·	It is anticipated that a professional building management team headed by a Project Executive will be responsible for the day to day operations of the total physical plant.  Sales and marketing efforts will be interfaced with the team.

·	A fully computerized building management and operations system will be utilized in a direct accountability format to assign costs to the appropriate tenants and use.

LEASING AND RENTALS

·	Leasing of commercial areas will be coordinated with the Project Executive and his staff.  It is anticipated that commercial leases will be executed by outside leasing agents and coordinated with in-house personnel.

·	Leases will be on a net/net/net basis.

·	A timeshare rental program will be continuously in effect to utilize available units and maximize revenue until such time as all available units are sold out.   It will be coordinated as a part of the overall building management effort.

PARKING

·	Each unit will be provided with parking .  Also, commercial parking will be provided for other usage.  The final parking accommodations will be organized for maximum user accessibility and ongoing project profitability.

GENERAL DESIGN AND CONSTRUCTION CONCERNS:

DESIGN:

It is assumed that the development will have fully rented commercial facilities on the ground floor.  These facilities will be designed to complement the overall apartment and condominium environment.  It is pictured that a full service health club and spa facility will be operated to service the entire facility.  Several restaurant facilities will be included in the complex (ranging from large to small); providing luxury appointments and also facilitating the provision of "room service" in one form or another.

CONSTRUCTION:

The construction of this project will provide for fire rated construction and fully sprinkled floors, and will provide the latest and best security for all occupants.

PROJECT EQUITY AND OWNERSHIP:

The ownership of the project is in the name of a new Limited Liability Company set up exclusively for this project (i.e.: WN Group, LLC).  The subject of whether further legal entities may be beneficial to hold properties with a continuous income stream separate and apart from the one-time sales properties is pending the advice of counsel

PARTICIPANTS:

Barnhard Realty Company

910 27th Street, N.W.

Washington, D.C.

Principals and Owners:   Ruby Barnhard

Dale Barnhard

Barnhard Realty has over 30 years experience in the Washington, D.C. market, specifically in the Watergate and Foggy Bottom areas of Northwest Washington, D.C.  They are key to the success of developing the overall project.  The properties in 1A, 1B, and 1C are owned by Barnhard Realty;  they lay in the center of the to be assembled area.  In order to develop Phases II and III, Barnhard's property plays a  central role.  In addition, Dale Barnhard is well connected to the leadership of the D.C. government and has served on the ANC for this ward for many years.  Negotiations and the requisite approvals that will be needed as the project progresses and will be expedited through Barnhard's personal contacts and network of people in government.

Barnhard Realty will be an equity partner in this venture.  Their property rights and interests would become a part of this overall development with these interests being subordinated to permit financing arrangements to proceed.

Gibson & Associates

1819 North Hollister Street

Arlington, VA 22205

Gibson & Associates has developed the enclosed analysis on this project and is ready to begin the design once the land use approvals process are in place and a full commitment for the project exists.  G&A will provide all A/E Services for the project including construction observation.  G&A will assign portions of the design effort and production to HSMM Inc. for Phase I of the project and reserves assignment for future assignments for other phases.  All development services will be provided by G&A and it’s development partners.

Gibson & Associates,, offers a fully integrated professional architecture and construction management practice.  G&A has previously participated in the development of large scale residential and commercial projects.  G&A is committed to design excellence with a thorough capability in project management and is committed to the timely completion of design for its clients.  The timely delivery of the project submittals is accomplished by monitoring and controlling the detailed work plan.  Methods and management are in place to guarantee results and time schedules. The goals of the firm simply stated are:

-Client Satisfaction.

-Design of an enduring quality.

-Working within the constraints of time and budget.

-Providing the best expertise for the design at hand.

-Understanding the Client's mission at all times.

G&A can provide the project with the most competent architectural and engineering design services, fully coordinated and delivered within the given constraints of budget and schedule.